## Sheet1
Task | Status | Start_Date_DateFormat | Due_Date | Start | Start_Date | Duration | Note
Form Team (All: Done) | Done | 2019-09-13 | 2019-09-20 | 0 | 43721 | 7
Brainstorm Ideas (All: Done) | Done | 2019-09-13 | 2019-10-05 | 0 | 43721 | 22
Create OMDB API Script (Jonathan: Done) | Done | 2019-09-13 | 2019-10-05 | 0 | 43721 | 22
Download Movielens (All: Done) | Done | 2019-09-13 | 2019-10-05 | 0 | 43721 | 22
Download OMDB (Yi: Done) | Done | 2019-09-13 | 2019-10-05 | 0 | 43721 | 22
Experimental Coding (Daniel, Yi: Done) | Done | 2019-09-13 | 2019-10-05 | 0 | 43721 | 22
Coallate MovieLens and OMBD Data (Jonathan) |  | 2019-09-20 | 2019-10-16 | 7 | 43728 | 26
========Project Proposal Due (All)======== |  | 2019-09-20 | 2019-10-11 | 7 | 43728 | 21
>LaTeX Compile & Submission: Rocko |  | 2019-09-20 | 2019-10-11 | 7 | 43728 | 21
>Paper: All |  | 2019-09-20 | 2019-10-11 | 7 | 43728 | 21
>Slides: Rocko |  | 2019-09-20 | 2019-10-11 | 7 | 43728 | 21
>Video: Daniel |  | 2019-09-20 | 2019-10-11 | 7 | 43728 | 21
=======Implement MovieExplorer======== |  | 2019-10-11 | 2019-10-23 | 28 | 43749 | 12
>Understand MovieExplorer Code/Algo |  | 2019-10-11 | 2019-10-13 | 28 | 43749 | 2
>Implement Exploration Code (no UI) (Yi, Rocko) |  | 2019-10-13 | 2019-10-23 | 30 | 43751 | 10 | Midterm
======Collaborative Filtering Engine====== |  | 2019-10-11 | 2019-10-20 | 28 | 43749 | 9
>Implement Matrix Factor Algo (Jonathan) |  | 2019-10-11 | 2019-10-20 | 28 | 43749 | 9 | Midterm
>Implement Word2Vec Algo (Daniel, Yi) |  | 2019-10-11 | 2019-10-20 | 28 | 43749 | 9 | Midterm
=======Visualization Preprocessing======= |  | 2019-10-20 | 2019-11-03 | 37 | 43758 | 14
>Embed Movies in Taste Space |  | 2019-10-20 | 2019-10-30 | 37 | 43758 | 10
>Implement TSNE (Rocko, Jonathan) |  | 2019-10-30 | 2019-11-03 | 47 | 43768 | 4 | Midterm
>Pre-cluster movies (Rocko, Jonathan) |  | 2019-10-30 | 2019-11-03 | 47 | 43768 | 4
==========Progress Report (All)========== |  | 2019-10-11 | 2019-11-08 | 28 | 43749 | 28 | Final
============Algorithm Polish============ |  | 2019-11-08 | 2019-11-22 | 56 | 43777 | 14 | Final
>GUI initial build (All) |  | 2019-11-08 | 2019-11-22 | 56 | 43777 | 14
>Plot projected movies (All) |  | 2019-11-08 | 2019-11-15 | 56 | 43777 | 7
>GUI Refinement (All) |  | 2019-11-15 | 2019-11-29 | 63 | 43784 | 14
==============Final Report============== |  | 2019-11-15 | 2019-11-29 | 63 | 43784 | 14 | Final
>Final Shared Poster (Rocko) |  | 2019-11-15 | 2019-11-22 | 63 | 43784 | 7 | Final
>Peer Grading (each of us, individually) |  | 2019-11-15 | 2019-11-22 | 63 | 43784 | 7 | Final
>Video (each of us, individually) |  | 2019-11-15 | 2019-11-22 | 63 | 43784 | 7 | Final
| 2019-10-04 11:00 |  | 2019-10-06 08:59
FALSE | 2019-10-06 09:14

## Jon's Recommendations
What | Who | When
Proposal | Rocko | 2019-10-13
Collate movielens, OMDB data | Jonathan | 2019-10-16
Collaborative filtering engine
Matrix factorisation | Jonathan | 2019-10-20
Word2vec | Daniel | 2019-10-20
Implement MovieExplorer
Understand MovieExplorer code/algo | Yi | 2019-10-13
Implement Exploration code (no UI) | Yi, Rocko | 2019-10-23
Vis - preprocessing
Embed movies in taste space | Daniel,Yi | 2019-10-30
T-SNE projection | Rocko, Jonathan | 2019-11-03
Pre-cluster movies | Rocko, Jonathan | 2019-11-03
Progress Report
Write progress report | All | 2019-11-08
Visualisation and Interface
Plotting projected movies | All | 2019-11-15
GUI intial build | All | 2019-11-22
GUI refinement | All | 2019-11-29
Final Report
Write final report and poster | All | 2019-11-29