## Sheet1
Task | Status | Start_Date_DateFormat | Due_Date | Start | Start_Date | Duration | Note
Form Team (All: Done) | Done | 2019-09-13 | 2019-09-20 | 0 | 43721 | 7
Brainstorm Ideas (All: Done) | Done | 2019-09-20 | 2019-10-11 | 7 | 43728 | 21
Download Movielens (All: Done) | Done | 2019-09-20 | 2019-10-11 | 7 | 43728 | 21
Download OMDB (All: Done) | Done | 2019-09-20 | 2019-10-11 | 7 | 43728 | 21
Experimental Coding (Daniel, Yi: Done) | Done | 2019-09-20 | 2019-10-11 | 7 | 43728 | 21
========Project Proposal Due (All)======== |  | 2019-09-20 | 2019-10-11 | 7 | 43728 | 21
>Paper: All |  | 2019-09-20 | 2019-10-11 | 7 | 43728 | 21
>Slides: Rocko |  | 2019-09-20 | 2019-10-11 | 7 | 43728 | 21
>Video: Daniel |  | 2019-09-20 | 2019-10-11 | 7 | 43728 | 21
>LaTeX Compile & Submission: Rocko |  | 2019-09-20 | 2019-10-11 | 7 | 43728 | 21
==========Recommender System========= |  | 2019-10-11 | 2019-11-01 | 28 | 43749 | 21
Opt 1: Implement Word2Vec Algo (Daniel, Yi) |  | 2019-10-11 | 2019-11-01 | 28 | 43749 | 21 | Midterm
Opt 2: Implement Matrix Factor Algo (Jonathan, Yi) |  | 2019-10-11 | 2019-11-01 | 28 | 43749 | 21 | Midterm
Implement TSNE (Jonathan) |  | 2019-10-11 | 2019-11-01 | 28 | 43749 | 21 | Midterm
D3 Skeleton (Rocko) |  | 2019-11-01 | 2019-11-08 | 49 | 43770 | 7 | Midterm
==========Progress Report (All)========== |  | 2019-10-11 | 2019-11-08 | 28 | 43749 | 28 | Final
D3 Polish (All?) |  | 2019-11-08 | 2019-11-15 | 56 | 43777 | 7 | Final
============Algorithm Polish============ |  | 2019-11-08 | 2019-11-15 | 56 | 43777 | 7 | Final
>Word2Vec (Yi, Daniel) |  | 2019-11-08 | 2019-11-15 | 56 | 43777 | 7
>Matrix Factor (Yi, Jonathan) |  | 2019-11-08 | 2019-11-15 | 56 | 43777 | 7
>TSNE (Jonathan, Rocko) |  | 2019-11-08 | 2019-11-15 | 56 | 43777 | 7
==============Final Report============== |  | 2019-11-15 | 2019-11-22 | 63 | 43784 | 7 | Final
>Video (each of us, individually) |  | 2019-11-15 | 2019-11-22 | 63 | 43784 | 7 | Final
>Final Shared Poster (Rocko) |  | 2019-11-15 | 2019-11-22 | 63 | 43784 | 7 | Final
>Peer Grading (each of us, individually) |  | 2019-11-15 | 2019-11-22 | 63 | 43784 | 7 | Final

## timeline2
What | Who | When
Proposal | Rocko | 2019-10-13
Collate movielens, OMDB data | Jonathan | 2019-10-16
Collaborative filtering engine
Matrix factorisation | Jonathan | 2019-10-20
Word2vec | Daniel | 2019-10-20
Implement MovieExplorer
Understand MovieExplorer code/algo | Yi | 2019-10-13
Implement Exploration code (no UI) | Yi, Rocko | 2019-10-23
Vis - preprocessing
Embed movies in taste space | Daniel,Yi | 2019-10-30
T-SNE projection | Rocko, Jonathan | 2019-11-03
Pre-cluster movies | Rocko, Jonathan | 2019-11-03
Progress Report
Write progress report | All | 2019-11-08
Visualisation and Interface
Plotting projected movies | All | 2019-11-15
GUI intial build | All | 2019-11-22
GUI refinement | All | 2019-11-29
Final Report
Write final report and poster | All | 2019-11-29

## Sheet2
Task | Days_Since_Start | Days_Left
Form Team | 0 | 7
Brainstorm Ideas | 7 | 21
Download Movielens | 7 | 21
Download OMDB | 7 | 21
Proposal Due | 7 | 21
Option 1: Implement Word2Vec Algo | 28 | 21
Option 2: Implement Matrix Factorization Algo | 28 | 21
Implement TSNE | 28 | 21
D3 Skeleton | 49 | 7
Progress Report | 28 | 28
D3 Polish | 56 | 7
Algorithm Polish | 56 | 7
Final Report | 63 | 7